## PSTN
Feature | Requirements lock date | Design completion date | UX Design ETA | Privacy review | Security reviews | Code start date | Azure Review | Code completion date | Testing | Bug fixing | Deployment | Status Note | Blockers | Dependencies | Action items with owners
[ACS][OPS] Introduce new flag in CDR to identify OPS calls | N/A |  |  |  |  | Dec 13, 2023 |  |  |  |  | N/A | 20/11/2024 - Awaiting completion of work to publish Resource Account Info to EERS from APS and exposing it on RAPI
[ACS][OPS] [DR][DO] CCTS Enhancements to cover new scenarios and flows OUTBOUND Calling (MVP1 RT3) | N/A |  |  |  |  | Nov 20, 2024 |  |  |  |  | Dec 22, 2024 | 24/12/17 - manual tests done and verified. CCTS automated tests blocked by DNS lockdown till 6th of January 2025 (we need DNS changes to setup new OBO tests)
[ACS][SIP] Send X-headers in outbound REFER | N/A |  |  |  |  | Nov 07, 2024 |  |  |  |  | Nov 24, 2025 | 28/8/2024 - Expectation is to get this code complete by 1st or 2nd week in Dec, but due to deployment freeze, rollout might take it into early January
[ACS][Calling SDK] Validate & Document UUI/X-headers for AddParticipant & Group Calls | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[ACS][PSTN][SIP] Expose call flows in CDC | Jul 26, 2024 |  |  |  |  | N/A |  |  |  |  | N/A
Migrate DR Number Assignment to TNM [Cleanup old code and db schemas] | N/A |  |  |  |  | Feb 22, 2024 |  |  |  |  | Jan 19, 2025
[R-API][ACS Call Settings][Auto-recording] Flexible calling runtime policies | Jun 28, 2024 |  |  |  |  | Sep 05, 2024 |  |  |  |  | Dec 22, 2024
[EERS][ACS Call Settings][Auto-recording] Flexible calling runtime policies | Jun 28, 2024 |  |  |  |  | Sep 05, 2024 |  |  |  |  | Dec 22, 2024 | 22/11/2024 Rollout in Progress and currently in Ring 3. Deployment was paused due to Cosmic APAC issue, and resumed on 21/11. ETA for full rollout is 5/12/24
[Metadata Store][ACS Call Settings][Auto-recording] Flexible calling runtime policies | Jun 28, 2024 |  |  |  |  | Sep 05, 2024 |  |  |  |  | Dec 22, 2024 | 20/11/2024 - Awaiting release of PubSub changes to Prod. EAT for PubSub release: 22/11/2024
[ACS][PSTN] Onboard Synthetics to DogFood | N/A |  |  |  |  | Aug 13, 2024 |  |  |  |  | N/A | 15/8/2024 - deprioritizing. primary focus on calling settings for now
SIP X-Header support- Incoming and Transfer | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Dynamics] Unified Customer-Friendly Call End Reason Phrases | N/A |  |  |  |  | N/A |  |  |  |  | N/A
Dummy Feature 2 | Nov 21, 2024 |  |  |  |  | Nov 25, 2024 |  |  |  |  | Jan 05, 2025
Dummy 3 | N/A |  |  |  |  | N/A |  |  |  |  | N/A
Dummy feature 4 | Dec 09, 2024 |  |  |  |  | Jan 22, 2025 |  |  |  |  | Mar 30, 2025
Dummy Feature 5 | Dec 13, 2024 | Feb 16, 2025 | Jan 05, 2025 | Dec 22, 2024 | Jan 05, 2025 | Dec 09, 2024 | Jan 19, 2025 | Feb 02, 2025 | Feb 02, 2025 | Jan 19, 2025 | Mar 02, 2025

## Call Automation_Signaling
Feature | Requirements lock date | Design completion date | UX Design ETA | Privacy review | Security reviews | Code start date | Azure Review | Code completion date | Testing | Bug fixing | Deployment | Status Note | Blockers | Dependencies | Action items with owners
[Error codes] Implement consistent code/subcode functionality between Call Automation and Client Calling | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[ACS] [Reliability] [P2] Safe Change Management - Testing <Call Automation Signaling> | N/A |  |  |  |  | Apr 25, 2024 |  |  |  |  | N/A | 6/28/2024 - We've moved our testing to improved framework . Once all GA branches covered, will do new review with Grisha. 3/27/2024 - Currently team is investing into CCTS testing setup reliability and making it more streamlined for adding new tests. This work is tracked under separate KTLO feature.
💍[OPS][Call automation] [Private Preview] As a CCaaS app, I can place basic outbound calls using Teams phone numbers | Nov 06, 2023 |  |  |  |  | Jun 20, 2024 |  |  |  |  | Feb 16, 2025 | 2024-11-20 [Complete] PMA implementation, ALPHA SDKs [Complete] Privacy & Security reviews [In Progress] CCTS, monitoring, internal documentation 8/7/2024 [Complete] Implementation complete in PMA for basic outbound [InProgress] Validating Redirect and Transferring [InProgress] Privacy review and other DoD items [Not started] alpha3 SDK release [Not started] CCTS tests
KR - Increase Call Automation SLA to 99.999% | N/A |  |  |  |  | N/A |  |  |  |  | N/A
💍[OPS][Call automation] [Private Preview] As a CCaaS app, I can support On-behalf-of (OBO) calls | N/A |  |  |  |  | Jun 10, 2024 |  |  |  |  | Feb 16, 2025 | 2024-11-20
[Horizontals] Quality/Latency : AddParticipant TimeToRing | N/A |  |  |  |  | Sep 05, 2023 |  |  |  |  | N/A
💍[OPS][ACS][Call Automation] New MRI support for OPS | N/A |  |  |  |  | Nov 20, 2024 |  |  |  |  | Feb 16, 2025 | 2024-12-16
💍[GA][OPS]Release Call automation support for OPS in general availability | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Preview] Add DeltaRoster with RemoteParticipantLeaveReasons | N/A |  |  |  |  | N/A |  |  |  |  | N/A | Still looking for new solutions on how this will be done on platform.
🔧[Eng improvements] [P2] CY24H2 Developer experience improvements & feature bugs | N/A |  |  |  |  | Jun 29, 2024 |  |  |  |  | N/A | Follows CY24H1 feature Feature 3533664
[Infra] Test and Verify IPV6 support - CallAutomation | N/A |  |  |  |  | N/A |  |  |  |  | N/A | Shared Infra
[ACS Durable Identities] Call automation support for new Entra External ID ACS users | N/A |  |  |  |  | N/A |  |  |  |  | N/A
📉 [Horizontals][Latency - 1] Route Incoming ACS PSTN calls to PMA | N/A |  |  |  |  | Sep 11, 2024 |  |  |  |  | Mar 02, 2025 | 2024-11-20:
📉 [Horizontals][Latency] Telemetry for call setup events | N/A |  |  |  |  | Sep 18, 2024 |  |  |  |  | N/A | 2024-11-20:
📉 [Horizontals][Latency - 2] Improve latency of calls auto-routed to PMA | N/A |  |  |  |  | Oct 22, 2024 |  |  |  |  | N/A | 2024-11-20
📉 [Horizontals][Latency - 5] Incoming call notifications via callback URL - OPS Flow | N/A |  |  |  |  | Nov 25, 2024 |  |  |  |  | Feb 16, 2025
[Dynamics Intake][Fundamentals] Provide a response for every API call | Jan 31, 2024 |  |  |  |  | N/A |  |  |  |  | N/A
📉 [Horizontals][Latency - 6] Region affinity for PMA and MPaaS instances | N/A |  |  |  |  | Nov 22, 2024 |  |  |  |  | Mar 02, 2025
🤖 [Teams AA IVR] Dynamics IVR support for Teams Auto Attendant | N/A |  |  |  |  | Nov 12, 2024 |  |  |  |  | N/A
📉[Horizontals] Measure and report on latency metrics | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[ACS-CA] Support 10K Concurrent Calls by Apr 2025 | N/A |  |  |  |  | N/A |  |  |  |  | N/A
🤖 [Teams AA IVR] Cognigy IVR support for Teams Auto Attendant | N/A |  |  |  |  | Nov 12, 2024 |  |  |  |  | N/A
🔧[Eng improvements] [P2] CY25-H1 Developer experience improvements & feature bugs | N/A |  |  |  |  | Jan 01, 2025 |  |  |  |  | N/A | Follows CY24H1 feature Feature 3533664
📉 [Horizontals][Latency] Load test setup | N/A |  |  |  |  | N/A |  |  |  |  | N/A
🛠️[Eng improvements] [P2] CY24-H2 Repair items for outages and operational incidents | N/A |  |  |  |  | Nov 22, 2024 |  |  |  |  | N/A
🛠️[Eng improvements] [P2] CY25-H1 Repair items for outages and operational incidents | N/A |  |  |  |  | N/A |  |  |  |  | N/A
📉 [Latency][Outbound calling] PSTN callee Answer to ParticipantsUpdated Event - Design only | N/A |  |  |  |  | N/A |  |  |  |  | N/A
💍[OPS][GA] Support OC for blind transfer to Teams agent and drops off | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[DOC] CA Documentation Improvements | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Dynamics] SIP X-Header support- Incoming and Transfer | N/A |  |  |  |  | N/A |  |  |  |  | N/A

## Call Automation_Media
Feature | Requirements lock date | Design completion date | UX Design ETA | Privacy review | Security reviews | Code start date | Azure Review | Code completion date | Testing | Bug fixing | Deployment | Status Note | Blockers | Dependencies | Action items with owners
[Hold Support (Group Call)] Resume music on hold from where it was stopped | Apr 29, 2024 |  |  |  |  | Oct 17, 2024 |  |  |  |  | Dec 22, 2024
[Private] Cancel specific media operation | Dec 01, 2023 |  |  |  |  | N/A |  |  |  |  | N/A
[Public Preview] Exposed enhanced media metrics to ACS customers | Jan 31, 2024 |  |  |  |  | N/A |  |  |  |  | N/A
[Public Preview] Sentiment analysis | Apr 26, 2024 |  |  |  |  | N/A |  |  |  |  | N/A
[Public Preview] Enhance recognize with Intent classification | Apr 26, 2024 |  |  |  |  | N/A |  |  |  |  | N/A
[GA-TBD][MPaaS Tracking] IP Range allow-listing for Call Automation media features | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[GA] Update the recognize logic to calculate timeout value dynamically based on length of prompt provided | Apr 19, 2024 |  |  |  |  | N/A |  |  |  |  | N/A
[GA-TBD] Real-time transcription | N/A |  |  |  |  | Aug 21, 2024 |  |  |  |  | N/A
ACS Reliability commitments | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Dynamics] Bidirectional Audio Streaming | Apr 26, 2024 |  |  |  |  | N/A |  |  |  |  | N/A
[Eng Improvements] Call Automation Media - Telemetry - Internal PMA Sync/Async results | N/A |  |  |  |  | Feb 20, 2024 |  |  |  |  | Dec 22, 2024
[GA][Eng Improvements] Increase the limit for Play text form 400 to higher | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Eng Improvements] Recognize - Improve Barge-In delay to 1second range | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Private preview] Support updating Azure AI resource during call (Cognitive service regional failure handling) | Apr 20, 2024 |  |  |  |  | Oct 17, 2024 |  |  |  |  | N/A | Cognitive service regional failure handling
[Private preview] PII redaction for transcription | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Public Preview] Language detection for recognize | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Public Preview] Language detection for Transcription | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[GA5] Bi-di Audio Streaming | N/A |  |  |  |  | Aug 13, 2024 |  |  |  |  | N/A
[GA4] Media features (Play Improvements, Hold/Unhold) | N/A |  |  |  |  | Aug 21, 2024 |  |  |  |  | Nov 24, 2024
[Calling Media] Migrate to RP-Client-Library from ResourceIdMappingLib | N/A |  |  |  |  | N/A |  |  |  |  | N/A
Play and Recognize SLA at 99.999% reliability | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[GA5] Auth for web socket connection | N/A |  |  |  |  | Aug 21, 2024 |  |  |  |  | Dec 22, 2024
[GA5] Customer telemetry for media streaming and transcription | N/A |  |  |  |  | Oct 18, 2024 |  |  |  |  | N/A
[GA-TBD][Transcription] Custom SR model | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Enhancements] Bot audio in transcript | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Private Preview] Participant filtering | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Public Preview] Mixed Media streaming and transcription | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Dynamics] Support 5K/10K Concurrent calls with Transcription | N/A |  |  |  |  | Aug 27, 2024 |  |  |  |  | Jan 05, 2025
[POC/Private Preview] Native Open AI Integration | N/A |  |  |  |  | N/A |  |  |  |  | N/A
Mid-call/end-call recap using transcription | N/A |  |  |  |  | N/A |  |  |  |  | N/A | Concept and Scenarios: 2409-ACS Call Recap and other Value-Added Features using Transcription.docx
[Fundamentals] MPaaS IVR session HA | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Fundamentals] Support of bidirectional media steaming. | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Tracking] HADR for MPaaS IVR failover - Play/Recognize | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Dynamics] Port Hold/Unhold to Dynamics specific version | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[GA] Include Bot Prompts in Recognize in Recording when there are only 2 real participants in the call | N/A |  |  |  |  | N/A |  |  |  |  | Oct 13, 2024 | 10/18- Onboarding Schindler customer WW in production to the feature
[Dynamics] Support for 40k concurrent calls with transcription | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Latency Improvements] Call Connection time improvements - Ability to set media streaming/transcription/cogsvc token outside of MPaaS AddParticipant API | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Latency Improvements] Reduce Stop Transcription API delay to less than 250ms | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[OPS] GA support for Media Streaming/Transcription and AI Actions | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[GA5] Pass CallConnectionId and CorrelationId in websocket and grpc headers during connection time | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[GA5-TBD] Bot self-audio for streaming | N/A |  |  |  |  | Aug 21, 2024 |  |  |  |  | Dec 22, 2024
[GA5] DTMF tones capture on streaming out without participant id | N/A |  |  |  |  | Aug 21, 2024 |  |  |  |  | Dec 22, 2024
[GA5-TBD] Initiate WebSocket connection form Contoso to IVR | N/A |  |  |  |  | Aug 21, 2024 |  |  |  |  | Dec 22, 2024

## Graph_Calling
Feature | Requirements lock date | Design completion date | UX Design ETA | Privacy review | Security reviews | Code start date | Azure Review | Code completion date | Testing | Bug fixing | Deployment | Status Note | Blockers | Dependencies | Action items with owners
[Compliance Recording] Slice of production to map to Teams rings for testing | N/A |  |  |  |  | N/A |  |  |  |  | N/A | COGS reduction
[T-Pre] Queues App Shared Call History - PMA Work | N/A |  |  |  |  | N/A |  |  |  |  | N/A | 4/21 status: not in CC plan for Q3. Might be a design discussion in H2.
Enforce Call Duration Limits on RT Media Access (includes captions, transcripts and recording) | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Design] Org Recording support to record calls | N/A |  |  |  |  | N/A |  |  |  |  | N/A | 9/24 - Discussions on org recording to be released as part of CY25H1 kicking off. Design in Q4
[Implementation] Organizational Recording support to record CQ agents | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Copilot] [Design] Enable 1:1 Call Copilot to escalate to group call and write Transcript to new chat thread | N/A |  |  |  |  | N/A |  |  |  |  | Dec 08, 2025 | 10/8 - This Design only feature slated for Q4 @Olga Kwasniewska & @Nitin Jaitely fyi
[Copilot] Implementation: Real Time Access to Live Captions to Beta customer | N/A |  |  |  |  | Aug 05, 2024 |  |  |  |  | Dec 08, 2025 | 9/3 - Waiting for throttling to be ready first.
[PMA Reliability] Achieve Five 9s of availability for all Tier 0 services by end of CY24 | N/A |  |  |  |  | May 13, 2024 |  |  |  |  | N/A | 9/30 - Resolved a lot of child items in Q4. Continue in Q4 and target to reach 5-9s by end of Q4.
CCTS coverage enhancement for PMA | N/A |  |  |  |  | Nov 01, 2024 |  |  |  |  | N/A | 9/6 - @Puya Daravi please seperate this effort in WW and Rest of the clouds and make use of Waferwire resourcing to unblock
[T-Pre] Recording Support for Production Studio | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[PMA] Net Core migration - Remaining work | N/A |  |  |  |  | Oct 15, 2024 |  |  |  |  | N/A | 12/9 - @Naveed Ali will collect ETA from Recorder team. For now it is blocked and moving to Q1.
[Teams] [Advanced Meeting Rooms] [Plaza] Fetch virtual Sourceid for multiple video payloads for Plaza | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Beta] Third-party meeting bots can start/stop a meeting transcriptions/recording for in call mode | N/A |  |  |  |  | Sep 27, 2024 |  |  |  |  | Dec 08, 2025
Scale down PMA to target for 30% CPU usage and release 15-20K vCores | N/A |  |  |  |  | Aug 19, 2024 |  |  |  |  | N/A | 11/20 - Considering the upcoming freezing, it needs more time to finish the scaling down. Moving to next quarter to continue.
[Compliance Recording] Enabling Pre-Prod Testing for ISV (Nice) | N/A |  |  |  |  | N/A |  |  |  |  | Dec 08, 2025
[Recording] Pass the information about meeting type to Bot | N/A |  |  |  |  | N/A |  |  |  |  | N/A | 11/4 - funded tentatively for Q1.
[Copilot] [Implementation] Enable 1:1 Call Copilot to escalate to group call and write Transcript to new chat thread | N/A |  |  |  |  | N/A |  |  |  |  | N/A
Recording Support for TownHall Queue in Managed Mode - meetingCapability.showContentSharePreviewInManagedMode | N/A |  |  |  |  | N/A |  |  |  |  | Dec 08, 2025 | Front loaded to Q1 (Mid Jan if possible). Frontload contract work in Q4 during freezing so Recorder can start work in parallels.
[PMA/ Graph Calling] Meet FR/DE NCOE Operations/Compliance Requirements by 5/15/25 | N/A |  |  |  |  | N/A |  |  |  |  | N/A
CR Perf improvement: Use GetConversation to fetch roster instead of rejoin converation | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[PLAT][KR-3][PMA] Onboard 100% of MVP services to Service Agnostification and Best Practices by 2/15/25 | N/A |  |  |  |  | Dec 11, 2024 |  |  |  |  | N/A
[T-Pre][PMA]AI Interpretation voice simulation consent | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[PMA]CR: Partial Roster Design and Implementation | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[AI] Graph/PMA Should Support Custom Content | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Copilot] Release: Real Time Access to Live Captions / Transcript to Beta | N/A |  |  |  |  | Aug 05, 2024 |  |  |  |  | N/A | 9/3 - Waiting for throttling to be ready first.

## Job Router
Feature | Requirements lock date | Design completion date | UX Design ETA | Privacy review | Security reviews | Code start date | Azure Review | Code completion date | Testing | Bug fixing | Deployment | Status Note | Blockers | Dependencies | Action items with owners
[Placeholder][OneVoice] ("Ask 5") Job Router - Telemetry and Metrics for Job Router | N/A |  |  |  |  | N/A |  |  |  |  | N/A | 2/8 - list of events were provided. Expecting feedback from Abhas.
Safe Change Management - Testing <Job Router> | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Cert Management] - Monitoring and Alerting of Certs <Job Router> | N/A |  |  |  |  | N/A |  |  |  |  | N/A
Monitoring and Alerting <Job Router> | N/A |  |  |  |  | Dec 11, 2022 |  |  |  |  | N/A
Design and implement Process Manager | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[AudioCodes] Enhance API to give developers ability to programmatically Enable/Disable simultaneous offers to agents. | N/A |  |  |  |  | Jan 21, 2024 |  |  |  |  | Apr 28, 2025
[CY24H1][SPoG][ACS] KR-2: <Job Router> Onboard all IC3 Tier 1 Services (51 services) aggregated success rate, latency, and volume with azure region dimension in SPoG by 2024-28-Jun. | N/A |  |  |  |  | Feb 27, 2024 |  |  |  |  | May 26, 2025
[AudioCodes] [GA]Enhance API to give developers ability to programmatically Enable/Disable simultaneous offers to agents. | N/A |  |  |  |  | Jan 21, 2024 |  |  |  |  | N/A
[Intake from Billing] Resiliency - Make Retry Logic for MSDK More Robust | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[APS] [ACS Platform][COSMIC-WS22+BaseImage] 100% of IC3 services on COSMIC migrate to WS22 nodes & COSMIC base images by 8/30/24 | N/A |  |  |  |  | Nov 09, 2024 |  |  |  |  | Sep 15, 2025
Job router Repair items CY2024/Q4 CY2025/Q1 | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[HPA Removal] JR support for POP+PFT on outbound to ATS | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[HPA Removal] JR support for POP+PFT on outbound to RP for getting resource model | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[HPA Removal] JR support for POP+PFT on outbound to Chronos | N/A |  |  |  |  | N/A |  |  |  |  | N/A

## Graph_Application Management
Feature | Requirements lock date | Design completion date | UX Design ETA | Privacy review | Security reviews | Code start date | Azure Review | Code completion date | Testing | Bug fixing | Deployment | Status Note | Blockers | Dependencies | Action items with owners
PlatformService RP - ConfigAPI Modernisation | N/A |  |  |  |  | Dec 12, 2023 |  |  |  |  | N/A | 12/12 - Code has been merged. Pending for rollout. Move out of current quarter.
[PlatformServiceRP] - Move to use NAS in GCCH & DoD for DR phone number assignments - phase 1 | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[APS Reliability] Achieve Five 9s of availability for all Tier 0 services by end of CY24 | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[OPS] APS to publish Bot MRI mappings to EERS | N/A |  |  |  |  | Aug 18, 2024 |  |  |  |  | Oct 13, 2025
[APS][All Clouds] Ensure we have full CCTS coverage for existing tests | N/A |  |  |  |  | Jun 03, 2024 |  |  |  |  | N/A | 10/8 - @Nathan Bennett can we do CCTS this quarter
[Secrets - ID 1.2] Cosmos DB v3 SDK with TLS1.2 required - APS | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[HPA Removal] APS support for POP+PFT on outbound to skype token service | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[HPA Removal] APS support POP+PFT on inbound traffic | N/A |  |  |  |  | N/A |  |  |  |  | N/A

## Calling_Captions
Feature | Requirements lock date | Design completion date | UX Design ETA | Privacy review | Security reviews | Code start date | Azure Review | Code completion date | Testing | Bug fixing | Deployment | Status Note | Blockers | Dependencies | Action items with owners
[Private preview] ACS Closed Captions - support translation and BYO-Cognitive Services | Jul 29, 2022 |  |  |  |  | N/A |  |  |  |  | N/A | 3/15 - Currently we are in technical design phase. ETA for Tech design 3/24
Recording Reliability improvements - Technical Debt, Issue with Pause/ Resume APIs, Scenario Reliability for Start Recording is less than 3 9s, Fix issues on GA APIs, Vendors to work on CCTS, Test Automation. | N/A |  |  |  |  | N/A |  |  |  |  | N/A

## Calling_Recording
Feature | Requirements lock date | Design completion date | UX Design ETA | Privacy review | Security reviews | Code start date | Azure Review | Code completion date | Testing | Bug fixing | Deployment | Status Note | Blockers | Dependencies | Action items with owners
[Private][AI][Call Recording] Smart Video Indexing | Aug 18, 2023 |  |  |  |  | N/A |  |  |  |  | N/A
[Captions and Transcripts] Engineering Design for Post-call Transcripts | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[AI] Call Transcription - Post-Call Transcript | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Dependency] Recording Team Support for ACS Transcription | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Private Preview] Teams Interop - Call Recording for Teams Hosted Meetings | Jan 31, 2023 |  |  |  |  | N/A |  |  |  |  | N/A | 3/14 - Due to an automation this feature was erroneously included for April releases. Call recording team will pick up this feature in Q3. It will remain in iteration path SPOOL until then.
[Technical debt] [Bugs] [Engineering Improvements] ACS Recording | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Private][AI][Call Recording] PCI and PII redaction | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Technical Debt] Improve Runners and Testing for ACS Recording | N/A |  |  |  |  | Sep 15, 2023 |  |  |  |  | N/A
ACS Call Recording in GCCH | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Call automation-OPS - ACS Recording] ACS Recording by CCaaS user for OPS | Nov 30, 2023 |  |  |  |  | Aug 14, 2024 |  |  |  |  | Nov 24, 2025
[Placeholder] GCCH work for programmable voice - Recording | N/A |  |  |  |  | N/A |  |  |  |  | N/A | 11/7 - Workplan started here GCCH workplan
[ACS Recording] [POC] Start Recording parameter when answering a call. | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[ACS Recording] [Private Preview] Start Recording parameter when answering a call. | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Gov cloud] [Captions] Support ACS closed captions in Gov cloud GCCH | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Sev 1 Event Service] [RecordingCompleteEvent] Users can query Recording API to get the AMS download URL | N/A |  |  |  |  | Nov 18, 2024 |  |  |  |  | Dec 08, 2025
[AI] PII redaction from ACS Recordings | N/A |  |  |  |  | N/A |  |  |  |  | N/A
Improve Reliability of Pause, Resume and Start Recording APIs by resolving known issues in end to end workflow. | N/A |  |  |  |  | N/A |  |  |  |  | N/A
Auto Recording for Outbound calls | N/A |  |  |  |  | N/A |  |  |  |  | N/A
Latency reduction to 250ms for pause and resume recording | N/A |  |  |  |  | N/A |  |  |  |  | N/A
OPS Public preview and GA readiness - Dual Personas, testing and other usecases for GA OPS Recording. | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[KTLO][FY25H2] Call Automation Recording - Repair Items from Previous incidents | N/A |  |  |  |  | N/A |  |  |  |  | N/A
Security Wave 4 ADO Items (Resources owned for CCTS, event grid, requests from AMS, Recorder Service, Gateway) | N/A |  |  |  |  | N/A |  |  |  |  | N/A
Horizontals work | N/A |  |  |  |  | N/A |  |  |  |  | N/A
Auto Recording Integration with Runtime API (CC and PMA pending changes, error handling, retries) | N/A |  |  |  |  | N/A |  |  |  |  | N/A
Latency Improvement, Optimization of bot setup in Auto Recording (media setup), Delta Roster to update Recorder state | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[AI] Summarization | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[AI] PII redaction from Post Call Transcription | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[AI] Chapters in Video Recording similar to Teams Recording | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[AI] Sentiment analysis of recording | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Spike] Video Recording Improvements about bitrate and fps (Work with IC3 recorder team on video settings) | N/A |  |  |  |  | N/A |  |  |  |  | N/A
[Intake from Billing] Resiliency - Make Retry Logic for MSDK More Robust | N/A |  |  |  |  | N/A |  |  |  |  | N/A
GA SDK releases (AMS Download URL API, StartRecording using connection ID) | N/A |  |  |  |  | N/A |  |  |  |  | N/A
Tech Design of Unmixed Video Recording in Mp4 format, Request from Teledoc, SAGO, PeopleCert | N/A |  |  |  |  | N/A |  |  |  |  | N/A